## Slide 1
BEMS — BS-6
Proposal
Scope of Work, Effort Estimate and Delivery Timeline — Plan 1
1

## Slide 2
PROPOSAL
Scope of Work
Work item
Included
Intent classification
On-prem LLM classifies every question as deterministic, retrieval, or hybrid before any call is made
Tool-calling integration
BS-1..BS-5 endpoints documented and exposed as callable tools; model selects and invokes the correct one
RAG infrastructure
Milvus (vector search) + MinIO (object storage) + TEI (self-hosted embedding) deployed on MCMC infrastructure
Document ingestion & OCR
User-driven upload — native text extraction, with a self-hosted OCR engine (PaddleOCR or a vision-language model) as fallback for scanned documents and images
Knowledge Layer
Persistent per-user memory (behaviour, interests, preferences) in the same Oracle database — written/read only via a governed API, scoped to each user
Answer labelling
Every response marks fact vs. knowledge vs. narrative, with source citation for retrieved content
Audit integration
Every API call and retrieval query logged with user, role, timestamp and question — feeding the existing audit trail (PS-2)
Chat interface
Conversational UI integrated into the BEMS front end
Out of scope for v1: the assistant taking any write/approval action; Plan 2 (Select AI) unless separately approved.
2

## Slide 3
PROPOSAL
Effort & Man-Day Estimate — Plan 1
Indicative, based on Plan 1 (tool-calling) scope. Refined once the endpoint list and model are confirmed.
Roles match the existing BEMS delivery team (Man-Days Plan) — no new hires.
Role
Focus
Man-days
Backend Engineers
Intent classifier, RAG infra (Milvus/MinIO/TEI), tool-calling wiring, Knowledge Layer API, OCR integration
90
Frontend Engineer
Chat interface, answer labelling, memory-aware context
12
Test Engineer
Test cases per intent path, accuracy evaluation, Knowledge Layer scoping tests, OCR accuracy sampling
20
DevOps Engineer
Deploy Milvus, MinIO, TEI and the OCR engine on MCMC's VMware VMs
15
Project Manager
Design review, governance sign-off, endpoint-priority coordination
12
Total: ~149 man-days
Approx. 10–12 calendar weeks, run in parallel with the core BEMS build. Excludes Plan 2 (Select AI), costed separately if approved.
3

## Slide 4
PROPOSAL
Timeline
Weeks 1–2
Discovery
Confirm endpoint scope, evaluate tool-calling models against the real catalogue
Weeks 2–5
RAG infrastructure
Deploy Milvus, MinIO, TEI and the OCR engine on-prem; build the intent classifier and Knowledge Layer
Weeks 4–8
Tool-calling integration
Document and wire BS-3, BS-5 first; extend to remaining endpoints
Weeks 8–10
Chat UI & labelling
Conversational interface, fact/knowledge/narrative labelling, audit integration
Weeks 10–12
Testing & hardening
Accuracy evaluation, security review, UAT
4